## Sprint 1
Project Name | Intelligence IT Job Finding
Module Name | Sprint 1
Development Team | C2SE.06
Start Date | 2024-03-06
End Date | 2023-03-25
| Sprint 1 Report | [19 empty] | Kết thúc nhiệm vụ
| No. | Member Name | Estimate | Actual | [16 empty] | Giờ làm thêm
| 1 | Tuan, Nguyen Anh | 62 | 74 | [16 empty] | Trễ
| 2 | Dat, Nguyen Thanh | 72 | 80 | [16 empty] | Chậm tiến độ
| 3 | Duyet, Pham The | 60 | 72 | [16 empty] | Trước thời hạn
| 4 | Tri, Le Minh | 58 | 70
| Total |  | 252 | 296
Estimate
Sprint 1 | Component | Task Name | Responsible Member | Estimate | Total | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25
| Initial | Sprint Planning Meeting | All | 16 | 16 | 0
|  | Create Sprint backlog for Sprint 1 | Tuan | 5 | 5 | 5 | 0
|  | Create Test Plan Document for Sprint 1 | Tuan | 5 | 5 | 5 | 5 | 0
|  | Create Database Document Sprint 1 | Dat | 6 | 6 | 6 | 6 | 0
| Design UI | Design UI Chat with Chatbot on the web application [Admin] | Tri | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Dashboard view [Admin] | Dat | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Interact with the chatbot to receive approriate suggestions | Dat | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Create RASA Chatbot Dashboard [Admin] | Duyet | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Rules Management | Tri | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Stories Management | Duyet | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Respones Management | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Intents Management | Tri | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Code | [Front End] Dashboard view [Admin] | Tri | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | [Front End] Chat with Chatbot on the web application [Admin] | Tuan, Tri | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Back End] Chat with Chatbot on the web application [Admin] | Dat | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
|  | [Back End] Dashboard view [Admin] | Duyet | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
|  | [Front End] Interact with the chatbot to receive approriate suggestions | Tuan | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Front End] Create RASA Chatbot Dashboard [Admin] | Tri | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Back End] Interact with the chatbot to receive approriate suggestions | Tuan | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Back End] Create RASA Chatbot Dashboard [Admin] | Tri | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Front End] Intens Management | Dat | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Front End] Rules Management | Duyet | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Back End] Intens Management | Dat | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Back End] Rules Management | Duyet | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Front End] Stories Management | Dat | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Front End] Responses Management | Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | [Back End] Stories Management | Duyet | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Back End] Responses Management | Duyet | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Testing | Testing for Sprint 1 | All | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Fix bugs | Fix bugs for Sprint 1 | All | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0
| Re-Testing | Re-Testing for Sprint 1 | All | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Release Sprint 1 | Sprint 1 Review Meeting | All | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Sprint 1 Retrospective | All | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  |  | Total | 252 | 252 | 236 | 231 | 220 | 205 | 196 | 196 | 188 | 156 | 150 | 132 | 126 | 108 | 102 | 88 | 80 | 64 | 64 | 16 | 8 | 0
Actual
Sprint 1 | Component | Task Name | Responsible Member | Actual | Total | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25
| Initial | Sprint Planning Meeting | All | 16 | 16 | 0
|  | Create Sprint backlog for Sprint 1 | Tuan | 5 | 5 | 5 | 0
|  | Create Test Plan Document for Sprint 1 | Tuan | 5 | 5 | 5 | 5 | 0
|  | Create Database Document Sprint 1 | Dat | 6 | 6 | 6 | 6 | 0
| Design UI | Design UI Chat with Chatbot on the web application [Admin] | Tri | 3 | 3 | 6 | 6 | 6 | 6 | 3
|  | Design UI Dashboard view [Admin] | Dat | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Interact with the chatbot to receive approriate suggestions | Dat | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Create RASA Chatbot Dashboard [Admin] | Duyet | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Rules Management | Tri | 3 | 3 | 6 | 6 | 6 | 6 | 3
|  | Design UI Stories Management | Duyet | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Respones Management | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Intents Management | Tri | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Code | [Front End] Dashboard view [Admin] | Tri | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 2
|  | [Front End] Chat with Chatbot on the web application [Admin] | Tuan, Tri | 12 | 12 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 4
|  | [Back End] Chat with Chatbot on the web application [Admin] | Dat | 10 | 10 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 4
|  | [Back End] Dashboard view [Admin] | Duyet | 10 | 10 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 4
|  | [Front End] Interact with the chatbot to receive approriate suggestions | Tuan | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4
|  | [Front End] Create RASA Chatbot Dashboard [Admin] | Tri | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4
|  | [Back End] Interact with the chatbot to receive approriate suggestions | Tuan | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4
|  | [Back End] Create RASA Chatbot Dashboard [Admin] | Tri | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Front End] Intens Management | Dat | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Front End] Rules Management | Tuan | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Back End] Intens Management | Dat | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4
|  | [Back End] Rules Management | Duyet | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Front End] Stories Management | Dat | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | [Front End] Responses Management | Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | [Back End] Stories Management | Duyet | 6 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4
|  | [Back End] Responses Management | Duyet | 8 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 4
| Testing | Testing for Sprint 1 | All | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Fix bugs | Fix bugs for Sprint 1 | All | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0
| Re-Testing | Re-Testing for Sprint 1 | All | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Release Sprint 1 | Sprint 1 Review Meeting | All | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Sprint 1 Retrospective | All | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  |  | Total | 252 | 252 | 280 | 275 | 264 | 255 | 240 | 234 | 234 | 226 | 192 | 168 | 146 | 126 | 114 | 102 | 96 | 68 | 64 | 16 | 8 | 0
|  |  |  | Estimate |  | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25
|  |  |  | Estimate | 252 | 236 | 231 | 220 | 205 | 196 | 196 | 188 | 156 | 150 | 132 | 126 | 108 | 102 | 88 | 80 | 64 | 64 | 16 | 8 | 0
|  |  |  | Actual | 252 | 280 | 275 | 264 | 255 | 240 | 234 | 234 | 226 | 192 | 168 | 146 | 126 | 114 | 102 | 96 | 68 | 64 | 16 | 8 | 0

## Sprint 2
Project Name | Intelligence IT Job Finding
Module Name | Sprint 2
Development Team | C2SE.06
Start Date | 2024-03-26
End Date | 2024-04-14
| Sprint 1 Report | [19 empty] | Kết thúc nhiệm vụ
| No. | Member Name | Estimate | Actual | [16 empty] | Giờ làm thêm
| 1 | Tuan, Nguyen Anh | 63 | [17 empty] | Trễ
| 2 | Dat, Nguyen Thanh | 81 | [17 empty] | Chậm tiến độ
| 3 | Duyet, Pham The | 66 | [17 empty] | Trước thời hạn
| 4 | Tri, Le Minh | 56
| Total |  | 266 | 0
Estimate
Sprint 2 | Component | Task Name | Responsible Member | Estimate | Total | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14
| Initial | Sprint Planning Meeting | All | 16 | 16 | 0
|  | Create Sprint backlog for Sprint 2 | Tuan | 5 | 5 | 5 | 0
|  | Create Test Plan Document for Sprint 2 | Tuan | 5 | 5 | 5 | 5 | 0
|  | Create Database Document Sprint 2 | Dat | 5 | 5 | 5 | 5 | 0
| Design UI | Design UI for Job posting Page | Tri | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI for Employer management | Tuan | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI for Candidate management | Tuan | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI for Job application management | Tri | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI for Job Apply Page | Tuan | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Message Page [Employer] | Tri | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Message Page [Candidate] | Tri | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Code | [Front End] for Job posting Page | Tuan | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
|  | [Front End] for Employer management | Tri | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
|  | [Back End] for Job posting Page | Dat, Duyet | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Back End] for Employer management | Duyet | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Front End] for Candidate management | Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Front End] for Job application management | Tuan | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Back End] for Candidate management | Duyet | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
|  | [Back End] for Job application management | Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Front End] for Job Apply Page | Tri | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
|  | [Front End] Message Page | Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Back End] for Job Apply Page | Duyet | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Back End] Message Page | Dat, Duyet | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
| Testing | Testing for Sprint 2 | All | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Fix bugs | Fix bugs for Sprint 2 | All | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0
| Re-Testing | Re-Testing for Sprint 2 | All | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Release Sprint 2 | Sprint 2 Review Meeting | All | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Sprint 2 Retrospective | All | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  |  | Total | 268 | 268 | 250 | 245 | 235 | 223 | 214 | 214 | 214 | 170 | 170 | 170 | 124 | 124 | 124 | 78 | 78 | 62 | 62 | 14 | 6 | 0
Actual
Sprint 2 | Component | Task Name | Responsible Member | Actual | Total | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14
| Initial | Sprint Planning Meeting | All | 16 | 16 | 0
|  | Create Sprint backlog for Sprint 2 | Tuan | 5 | 5 | 5 | 0
|  | Create Test Plan Document for Sprint 2 | Tuan | 5 | 5 | 5 | 5 | 0
|  | Create Database Document Sprint 2 | Dat | 5 | 5 | 5 | 5 | 0
| Design UI | Design UI for Job posting Page | Tri | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI for Employer management | Tuan | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI for Candidate management | Tuan | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI for Job application management | Tri | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI for Job Apply Page | Tuan | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Message Page [Employer] | Tri | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI Message Page [Candidate] | Tri | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Code | [Front End] for Job posting Page | Tuan | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
|  | [Front End] for Employer management | Tri | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
|  | [Front End] for Candidate management | Dat, Duyet | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Front End] for Job application management | Duyet | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Front End] for Job Apply Page | Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Front End] Message Page | Tuan | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Back End] for Job posting Page | Duyet | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
|  | [Back End] for Employer management | Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Back End] for Candidate management | Tri | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
|  | [Back End] for Job application management | Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Back End] for Job Apply Page | Duyet | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | [Back End] Message Page | Dat, Duyet | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
| Testing | Testing for Sprint 2 | All | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Fix bugs | Fix bugs for Sprint 2 | All | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0
| Re-Testing | Re-Testing for Sprint 2 | All | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Release Sprint 2 | Sprint 2 Review Meeting | All | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Sprint 2 Retrospective | All | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  |  | Total | 268 | 268 | 250 | 245 | 235 | 223 | 214 | 214 | 214 | 170 | 170 | 170 | 124 | 124 | 124 | 78 | 78 | 62 | 62 | 14 | 6 | 0
|  |  |  | Estimate |  | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14
|  |  |  | Estimate | 268 | 250 | 245 | 235 | 223 | 214 | 214 | 214 | 170 | 170 | 170 | 124 | 124 | 124 | 78 | 78 | 62 | 62 | 14 | 6 | 0
|  |  |  | Actual | 268 | 250 | 245 | 235 | 223 | 214 | 214 | 214 | 170 | 170 | 170 | 124 | 124 | 124 | 78 | 78 | 62 | 62 | 14 | 6 | 0

## Sprint 3
Project Name | Skin Diagno Tech
Module Name | Sprint 3
Development Team | C1SE.48
Start Date | 2022-11-09
End Date | 2022-12-04
Sprint 3 Report
| No. | Member Name | Estimate | Actual
| 1 | Tuan, Nguyen Anh | 70.5 | 70.5
| 2 | Vang, Nguyen Xuan | 73 | 73
| 3 | Huy, Nguyen Cong | 53 | 53
| 4 | Trung, Ha Nguyen Thanh | 40.5 | 84.5
| Total |  | 237 | 281
Estimate
Sprint 3 | Component | Task Name | Responsible Member | Estimate | Total | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04
| Initial | Sprint Planning Meeting | All | 16 | 16 | 0
|  | Create Sprint backlog for Sprint 3 | Tuan | 5 | 5 | 5 | 0
|  | Create Test Plan Document for Sprint 3 | Tuan, Huy, Vang | 6 | 6 | 6 | 0
|  | Create Database Document Sprint 3 | Huy, Vang | 5 | 5 | 5 | 0
| Design UI | Design UI [Doctor] Doctor information Page | Huy | 2 | 2 | 2 | 2 | 0
|  | Design UI [Doctor] Edit information Page | Huy | 2 | 2 | 2 | 2 | 0
|  | Design UI [Doctor] Account Page | Tuan | 3 | 3 | 3 | 3 | 0
|  | Design UI [Doctor] History Articles and Questions Page | Tuan | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI [User] Account Page | Tuan | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI [User] History Articles and Questions Page | Huy | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI [Admin] Searching Doctor | Vang | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI [Admin] View Dashboard | Tuan | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI [Doctor] Articles and Questions Management | Tuan | 2 | 2 | 3 | 3 | 3 | 3 | 0
| Design Testcase | Design Test Case [Doctor] Doctor information Page | Trung | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test Case [Doctor] Edit information Page | Trung | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test Case [Doctor] Account Page | Trung | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Design Test Case [Doctor] History Articles and Questions Page | Trung | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test Case [User] Account Page | Trung | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Design Test Case [User] History Articles and Questions Page | Trung | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Design Test Case [Admin] Searching Doctor | Trung | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Design Test Case [Admin] View Dashboard | Trung | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Design Test Case [Doctor] Articles and Questions Management | Trung | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Code | Code Front-end [Doctor] Doctor information Page | Tuan, Vang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Front-end [Doctor] Edit information Page | Tuan, Vang | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | Code Front-end [Doctor] Account Page | Tuan | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Front-end [Doctor] History Articles and Questions Page | Tuan, Vang | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | Code Front-end [User] Account Page | Tuan | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Front-end [User] History Articles and Questions Page | Tuan, Vang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Front-end [Admin] Searching Doctor | Tuan, Vang | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | Code Front-end [Admin] View Dashboard | Tuan, Vang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Front-end [Doctor] Articles and Questions Management | Tuan, Vang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Back-end [Doctor] Doctor information Page | Vang, Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Back-end [Doctor] Edit information Page | Vang, Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Code Back-end [Doctor] Account Page | Vang, Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Back-end [Doctor] History Articles and Questions Page | Vang, Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Code Back-end [User] Account Page | Vang, Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Back-end [User] History Articles and Questions Page | Vang, Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Back-end [Admin] Searching Doctor | Vang, Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Code Back-end [Admin] View Dashboard | Vang, Huy | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | Code Back-end [Doctor] Articles and Questions Management | Vang, Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Testing | Testing for Sprint 3 | All | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Fix bugs | Fix bugs for Sprint 3 | All | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0
| Re-Testing | Re-Testing for Sprint 3 | All | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Release Sprint 3 | Sprint 3 Review Meeting | All | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Sprint 3 Retrospective | All | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  |  | Total | 237 | 237 | 222 | 206 | 199 | 192 | 183 | 175 | 170 | 160 | 150 | 136 | 128 | 124 | 112 | 100 | 96 | 82 | 82 | 78 | 62 | 30 | 14 | 14 | 6 | 6 | 6 | 0
Estimate
Sprint 3 | Component | Task Name | Responsible Member | Estimate | Total | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04
| Initial | Sprint Planning Meeting | All | 16 | 16 | 0
|  | Create Sprint backlog for Sprint 3 | Tuan | 5 | 5 | 5 | 0
|  | Create Test Plan Document for Sprint 3 | Tuan, Huy, Vang | 6 | 6 | 6 | 0
|  | Create Database Document Sprint 3 | Huy, Vang | 5 | 5 | 5 | 0
| Design UI | Design UI [Doctor] Doctor information Page | Trung | 2 | 2 | 2 | 2 | 0
|  | Design UI [Doctor] Edit information Page | Trung | 2 | 2 | 2 | 2 | 0
|  | Design UI [Doctor] Account Page | Tuan | 3 | 3 | 3 | 3 | 0
|  | Design UI [Doctor] History Articles and Questions Page | Tuan | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI [User] Account Page | Tuan | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI [User] History Articles and Questions Page | Huy | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI [Admin] Searching Doctor | Vang | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI [Admin] View Dashboard | Tuan | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI [Doctor] Articles and Questions Management | Tuan | 2 | 2 | 3 | 3 | 3 | 3 | 0
| Design Testcase | Design Test Case [Doctor] Doctor information Page | Trung | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6
|  | Design Test Case [Doctor] Edit information Page | Trung | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6
|  | Design Test Case [Doctor] Account Page | Trung | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4
|  | Design Test Case [Doctor] History Articles and Questions Page | Trung | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6
|  | Design Test Case [User] Account Page | Trung | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4
|  | Design Test Case [User] History Articles and Questions Page | Trung | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6
|  | Design Test Case [Admin] Searching Doctor | Trung | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4
|  | Design Test Case [Admin] View Dashboard | Trung | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4
|  | Design Test Case [Doctor] Articles and Questions Management | Trung | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4
| Code | Code Front-end [Doctor] Doctor information Page | Tuan, Vang | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Code Front-end [Doctor] Edit information Page | Tuan | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code Front-end [Doctor] Account Page | Tuan | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Code Front-end [Doctor] History Articles and Questions Page | Tuan | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code Front-end [User] Account Page | Tuan | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Code Front-end [User] History Articles and Questions Page | Tuan, Vang | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Code Front-end [Admin] Searching Doctor | Tuan, Vang | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code Front-end [Admin] View Dashboard | Tuan, Vang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Front-end [Doctor] Articles and Questions Management | Tuan, Vang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Back-end [Doctor] Doctor information Page | Tuan | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Back-end [Doctor] Edit information Page | Vang, Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Code Back-end [Doctor] Account Page | Vang, Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Back-end [Doctor] History Articles and Questions Page | Vang, Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Code Back-end [User] Account Page | Vang, Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Back-end [User] History Articles and Questions Page | Vang, Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code Back-end [Admin] Searching Doctor | Vang, Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Code Back-end [Admin] View Dashboard | Vang, Huy | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | Code Back-end [Doctor] Articles and Questions Management | Vang, Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Testing | Testing for Sprint 3 | All | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Fix bugs | Fix bugs for Sprint 3 | All | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0
| Re-Testing | Re-Testing for Sprint 3 | All | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Release Sprint 3 | Sprint 3 Review Meeting | All | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Sprint 3 Retrospective | All | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  |  | Total | 237 | 237 | 259 | 243 | 236 | 229 | 220 | 220 | 220 | 208 | 187 | 169 | 151 | 135 | 133 | 113 | 100 | 82 | 82 | 78 | 62 | 30 | 14 | 14 | 6 | 6 | 6 | 0
|  |  |  | Estimate |  | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04
|  |  |  | Estimate | 237 | 222 | 206 | 199 | 192 | 183 | 175 | 170 | 160 | 150 | 136 | 128 | 124 | 112 | 100 | 96 | 82 | 82 | 78 | 62 | 30 | 14 | 14 | 6 | 6 | 6 | 0
|  |  |  | Actual | 237 | 259 | 243 | 236 | 229 | 220 | 220 | 220 | 208 | 187 | 169 | 151 | 135 | 133 | 113 | 100 | 82 | 82 | 78 | 62 | 30 | 14 | 14 | 6 | 6 | 6 | 0